## RoC
RECORDS OF CHANGES
# | Date | In Charge | Change Notes
1 | 2022-11-05 | Tung | app mockup design change
2 | 2022-11-05 | Phuc | database design change
3 | 2022-12-05 | An | change project's goal (chat app to online shop)
4 | 13/5 | Phong | edit document
5
6
7

## Product
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned
1 | Show foods products | Public | Medium | Show foods products currently selling in the home page | Iteration 1
2 | User Login | Common | Simple | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Iteration 1
3 | User Register | Common | Simple | This is a pop-up screen which allows the user to register to the system by inputing following information: full name, user title (Mr, Mrs, Ms,..), email, mobile, address; User then needs to verify by clicking the link sent via email to him/her before being able to access the system | Iteration 1
4 | User Profile | Common | Simple | This is a pop-up screen which allows the user to edit his/her profile information, including the registered user information and the avatar image (s/he is not allowed to change the email) | Iteration 4
5 | Change Password | Common | Simple | Allow users to change their password | Iteration 4
7 | About page | Common | Simple | (5 screen) : show information about history of the company , origin of products, suppliers, services offering | Iteration 3
7 | Cart system | Common | Medium | Show foods products currently in the users cart | Iteration 1
8 | Home Page | Common | Simple | Show new foods , best selling foods, | Iteration 2
9 | View Food details | Common | Medium | The user can click on a food items to view more information about: ingredients, price, size , | Iteration 3
10 | Food ordering | Common | Medium | Allow customer to order food . User can click on "add to cart" button under food items to add it to cart. | Iteration 2
11 | Payment system | Common | Medium | Allow customer to pay using card | Iteration 2
12 | Reset Password | Common | Medium | The user to input his/her email to receive the reset password link - On clicking the link, the user is redirected to the page in which s/he input new password (twice) - Note that the link is only available for a specific time duration as configured in the system config file. | Iteration 4
13 | Customer services\ | Common | Medium | Allow users to message admin for customer services | Iteration 4
14 | Show products by category | Common | Medium | show all products in a category | Iteration 2
15 | Show products by price | Common | Medium | show products by price (high to low, low to high) | Iteration 3
16 | Show products by date added | Common | Medium | show products by date added | Iteration 4
17 | User Authorization | Common | Complex | This is authorization mechanism in the system, including the specify the user's role, his/her authorized page links (building the displayed menu items and preventing unauthorized access via enter the links directly). The scope of this function also includes building the header, footer, the main function menu (for both Admin and NonAdmin parts) | Iteration 1
18 | Chatting system | Common | Complex | Allow users to chat with each other | Iteration 3
19 | Users List | Admin | Simple | Show the paginated list of registered users (include users' id, full name, user title, email, mobile, role, status): - The admin can filter the users by role, status - Allow the admin to seach users by full name, email, mobile - The list can be sortable by id, fullname, gender, email, mobile, role, status - From this page, the admin can choose to add new user, view or edit existing one, via the User Details screen below | Iteration 4
20 | Transactions history | Admin | Complex | Show detailed all transactions to admin | Iteration 4
| complex | >15 fields | > 7 transactions
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Iteration 1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 1 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 | Phong | Pending | Allow registered user to login
2 | User Register | Common | Simple | 60 | An | Pending | Allow new user to register
3 | User Authorization | Common | Complex | 240 | Thang | Pending | Allow user to use functionalities for them
4 | Home Page | Public | Medium | 120 | Tung | Pending | show all products that are currently selling
5 | Chatting System | Public | Complex | 240 | Phuc, Thang ,An | Pending | Allow user to chat with friends
6 | Chat History | Common | Complex | 240 | An, Thang | Pending | Show chat history
7 | Food ordering | Common | Medium | 120 | An, Phuc , Tung | Pending | Allow users to order and pay for food
8 | Admin management system | Admin | Medium | 120 | Phuc, Thang | Pending | Allow admin to manage all products, account
9 | Transaction history | Admin | Medium | 120 | Tung,Phuc | Pending | Show all history of transaction made by users

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 2 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 | Phong | Pending | Allow registered user to login
2 | User Register | Common | Simple | 60 | An | Pending | Allow new user to register
3 | User Authorization | Common | Complex | 240 | Thang | Pending | Allow user to use functionalities for them
4 | Home Page | Public | Medium | 120 | Tung | Pending | show all products that are currently selling
5 | Chatting System | Public | Complex | 240 | Phuc, Thang ,An | Pending | Allow user to chat with friends
6 | Chat History | Common | Complex | 240 | An, Thang | Pending | Show chat history
7 | Food ordering | Common | Medium | 120 | An, Phuc , Tung | Pending | Allow users to order and pay for food
8 | Admin management system | Admin | Medium | 120 | Phuc, Thang | Pending | Allow admin to manage all products, account
9 | Transaction history | Admin | Medium | 120 | Tung,Phuc | Pending | Show all history of transaction made by users

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 3 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 | Phong | Pending | Allow registered user to login
2 | User Register | Common | Simple | 60 | An | Pending | Allow new user to register
3 | User Authorization | Common | Complex | 240 | Thang | Pending | Allow user to use functionalities for them
4 | Home Page | Public | Medium | 120 | Tung | Pending | show all products that are currently selling
5 | Chatting System | Public | Complex | 240 | Phuc, Thang ,An | Pending | Allow user to chat with friends
6 | Chat History | Common | Complex | 240 | An, Thang | Pending | Show chat history
7 | Food ordering | Common | Medium | 120 | An, Phuc , Tung | Pending | Allow users to order and pay for food
8 | Admin management system | Admin | Medium | 120 | Phuc, Thang | Pending | Allow admin to manage all products, account
9 | Transaction history | Admin | Medium | 120 | Tung,Phuc | Pending | Show all history of transaction made by users

## Iteration 4
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 4 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 | Phong | Pending | Allow registered user to login
2 | User Register | Common | Simple | 60 | An | Pending | Allow new user to register
3 | User Authorization | Common | Complex | 240 | Thang | Pending | Allow user to use functionalities for them
4 | Home Page | Public | Medium | 120 | Tung | Pending | show all products that are currently selling
5 | Chatting System | Public | Complex | 240 | Phuc, Thang ,An | Pending | Allow user to chat with friends
6 | Chat History | Common | Complex | 240 | An, Thang | Pending | Show chat history
7 | Food ordering | Common | Medium | 120 | An, Phuc , Tung | Pending | Allow users to order and pay for food
8 | Admin management system | Admin | Medium | 120 | Phuc, Thang | Pending | Allow admin to manage all products, account
9 | Transaction history | Admin | Medium | 120 | Tung,Phuc | Pending | Show all history of transaction made by users