## RoC
RECORDS OF CHANGES
# | Date | In Charge | Change Notes
1 | 31/5 | An | Update home and signup page
2 | 2022-01-06 | Phong | Updated model package(category, users)
3 | 2022-01-06 | Thang | Config home page
4 | 2022-03-06 | An | Fix bug nhảy màn hình lên ở SignUp.jsp
5
6
7

## Product
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned
1 | User Login | Common | Simple | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Iteration 1 | medium | <=15 fields | <= 7 transactions
2 | User Register | Public | Simple | This is a pop-up screen which allows the user to register to the system by inputing following information: full name, user title (Mr, Mrs, Ms,..), email, mobile, address; User then needs to verify by clicking the link sent via email to him/her before being able to access the system | Iteration 1 | simple | <=7 fields | <=3 transactions
3 | User Authorization | Common | Complex | This is authorization mechanism in the system, including the specify the user's role, his/her authorized page links (building the displayed menu items and preventing unauthorized access via enter the links directly). The scope of this function also includes building the header, footer, the main function menu (for both Admin and NonAdmin parts) | Iteration 1 | complex | >15 fields | > 7 transactions
4 | Cart system | Common | Medium | Show foods products currently in the users cart | Iteration 2
5 | Show foods products | Public | Medium | Show foods products currently selling in the home page | Iteration 1 | (*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
6 | Home Page | Common | Medium | Show new foods , best selling foods, | Iteration 2 | In which:
9 | Menu Page | Public | Complex | >10 screen: show food products via category: breakfast, lunch, dinner, coffee, deserts . | Iteration 2 | fields: screen components or database table fields
8 | Food ordering | Common | Medium | Allow customer to order food . User can click on "add to cart" button under food items to add it to cart. | Iteration 2 | transactions: action buttons, user or database transactions
9 | Payment system | Common | Medium | Allow customer to pay using card | Iteration 2
10 | Show products by category | Common | Medium | show all products in a category | Iteration 2
8 | About page | Common | Simple | (5 screen) : show information about history of the company , origin of products, suppliers, services offering | Iteration 3
9 | View Food details | Common | Medium | The user can click on a food items to view more information about: ingredients, price, size , | Iteration 3
13 | Chatting system | Common | Complex | Allow users to chat with each other | Iteration 3
14 | Customer services | Common | Medium | Allow users to message admin for customer services | Iteration 3
15 | Users List | Admin | Simple | Show the paginated list of registered users (include users' id, full name, user title, email, mobile, role, status): - The admin can filter the users by role, status - Allow the admin to seach users by full name, email, mobile - The list can be sortable by id, fullname, gender, email, mobile, role, status - From this page, the admin can choose to add new user, view or edit existing one, via the User Details screen below | Iteration 4
16 | Transactions history | Admin | Complex | Show detailed all transactions to admin | Iteration 4
17 | Reset Password | Common | Medium | The user to input his/her email to receive the reset password link - On clicking the link, the user is redirected to the page in which s/he input new password (twice) - Note that the link is only available for a specific time duration as configured in the system config file. | Iteration 4
18 | User Profile | Common | Simple | This is a pop-up screen which allows the user to edit his/her profile information, including the registered user information and the avatar image (s/he is not allowed to change the email) | Iteration 4
19 | Change Password | Common | Simple | Allow users to change their password | Iteration 4
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Iteration 1
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 1 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | User Login | Common | Simple | 60 | Phuc | Done | Allow registered user to login
2 | User Register | Public | Simple | 60 | An | Done | Allow new user to register
3 | User Authorization | Common | Medium | 120 | Thang | Done | Allow user to use functionalities for them
4 | Home Page | Public | Medium | 120 | Phong | Done | Show home page of the website, images of products
5 | Menu Page | Public | Medium | 120 | Tung | Deferred | Show menu of products

## Iteration 2
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 2 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Payment system | Common | Medium | 120 | Thang, Phong | Pending | Allow user to pay with card info and save to database
2 | Chatting System | Common | Complex | 240 | Phuc,An | Pending | Allow user to chat with friends
3 | Cart System | Common | Medium | 120 | Thang , An | Pending | Allow user to check and use cart , save items intodatabase
4 | Admin page | Admin | Complex | 240 | Phong | Pending | Allow functionalities of admin
5 | Review page | Admin | Complex | 240 | Phuc,An | Pending | Product detail
6 | Edit | Admin | Complex | 240 | Phong | Pending | CRUD

## Iteration 3
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 3 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | About page | Public | Medium | 240 | Tung | Pending | Show about page of the app
2 | Food ordering | Common | Medium | 120 | An, Phuc | Pending | Allow users to order and pay for food
3 | Customer services | Common | Simple | 60 | Tung | Pending | Allow users to provide feedback and ask question regrading the services
4 | View food details | Public | Complex | 240 | Phong, Thang | Pending | >10 screen show detail info of a food product

## Iteration 4
THE APPLICATION DEVELOPMENT PROJECT TOPIC
ITERATION 4 BACKLOG
# | Function/Screen | Feature | Level* | LOC | In Charge | Status | Notes
1 | Admin management system | Admin | Medium | 120 | Phuc | Pending | Allow admin to manage all products, account
2 | Reset Password | Common | Simple | 60 | An | Pending | Allow users to reset their password in case they forgot
3 | User Profile | Common | Medium | 120 | Thang, | Pending | Allow user to manage thier info
4 | Transaction history | Admin | Medium | 120 | Phong | Pending | Show all history of transaction made by users