## Wx
Weekly report
Group | 5
Week 3 23/5
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details) | Quy tắc nhóm
1 | update SRS,SDD documents | Completed | Send for grading | 1. Tất cả mọi thành viên trong nhóm cùng code trung bình mỗi tuần 1 người 1 màn hình
2 | update the database | Completed | uploaded to group's github and merged to master | 2. Techleader kiểm tra code của mọi người hàng tuần
3 | Code log in, logout function | In Progress | 5 screen | 3. Một ngày các thành viên dành ra tối thiểu 2h/ngày để code, dành 15-30p để viết tài liêu, 10-15p để họp nhóm cùng nhau
4 | Code home page, menu page | In Progress | 10 screen total, in development | Cả nhóm phấn đấu code được 40-45 màn hình, 20-25 database table. Nguyên tắc để làm đi từ gốc của mindmap là tên đề tài sau đó là tên nhóm chức năng ( feature name-> screen namename -> vẽ screenFlow -> vẽ mockup màn hình -> vẽ database table diagram - vẽ package(AD) diagram. Thực chất chỗ này là khi hình dung ra tên của subject class sẽ được sắp xếp vào các folder của project. Detail design là cấu trúc bên trong class và mối quan hệ giữa các class = cách sử dụng class diagram. Mô tả giữa các class gọi nhau như thế nào thì mô tả qua sequence diagram
5 | Code sign up page | In Progress | still in development,
6 | Create weekly meeting minute | Completed | uploaded to drive | 4. hàng ngày meeting record phải ghi lại các issue và các solution
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete database design | AnKQ | 90% done
2 | Login, logout screen/ functions | PhucHN | 90%
3 | Home screen | Thang | need more work done
4 | Sign up page | AnKQ | needs team's agreement on class detail
5 | Menu screen | Tung | need more work done
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | 3 team member caught covid | In Progress | Put project on hold
2 | Lots of document need checking | In Progress | Slpit work to team
3
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish coding first iteration | 2022-03-06 | Login, logout, sign in, signup
2
3
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Following team member missing: Tung | AnKQ | Team member have not join meetings nor classes for 2 weeks
2
3